## Slide 1: CCP3014 – Individual Project
Project Proposal

## Slide 2: Today’s objectives
Overview of IT resources available to final-year students
To prepare to produce the Project Proposal
To answer questions from your reading of the handbook
To consider ethical issues associated with projects
To understand the ethics procedure

## Slide 3: Project Proposal
The definition of your project
Planning document
Yardstick against which project will be measured
The idea is NOT just to create a document…
  It’s to create a sound basis for your project
Build it well to avoid later problems.
Notes: The first major task is producing the Project Proposal – the full proposal for your project.

## Slide 4: Focus of Project
What this project is really all about.
Too small
Too hard
Too easy
Too big
What’s the real challenge ?
Is it clear?
Do some investigation
Be prepared to be flexible

## Slide 5
WRITE
Project Proposal
ARRANGE
Arrange meeting with supervisor & 2nd marker
REVIEW
Ethics Form (& any Risk Assessment)
Send documents at least 48 hrs before meeting.
Take your logbook – review form is in it
REVISE
Upload documents to Moodle by the due date
SUBMIT
Show to supervisor / 2nd marker as required
Get any outstanding approval
Discuss documents, get feedback
May get ethical approval
Make any changes required
Notes: The Project Proposal (and ethics) review process.
The Project Proposal review is an informal meeting, typically lasting about half an hour. It’s not a ‘presentation’, just a discussion. Be prepared to explain your ideas and receive feedback. We also use this meeting as an opportunity to give ethical approval for your project – but more of that later on.

## Slide 6: Project Proposal - Contents
Title
Background to Project
Proposed Work
Aims
Objectives
Skills
Sources of information / bibliography
Resources - hardware / software
Structure & contents of project report
Marking scheme
Project plan
and of course
YOUR NAME
etc. on cover page
Notes: These are the sections of the Project Proposal. We aren’t going to go through all of them.

## Slide 7: b. Background to Project
Main elements:
  Context of work
    Real-world context
    Subject context
  Reasons for work & why an interesting project
Needs background reading
Usually at least two pages.

## Slide 8: c. Proposed Work
  Why those?
  Further details of product or investigative work
  What’s literature review about?
  How will it help?
  What’s your approach?
  Bring out technical aspects
What will you do?
What’s the scope?
What
must you investigate?
What technologies will you
use?
Notes: This section explains what is involved in your project

## Slide 9: d. Aims
Aims state what the project should achieve; show project’s main purpose.
They are general
Usually 1 - 2 aims, occasionally 3.
  More is too many!
Make sure that it is the aims of the PROJECT that are explained not your personal goals
Your aims?

## Slide 10: e. Objectives
The way you achieve your aims!
Good objectives
  Have a specific outcome or deliverable
  Clear, NEVER vague – use action verbs
  Measurable & Concrete
Cover the whole project
A task or set of tasks will be associated with each objective

## Slide 11: S.M.A.R.T Objectives
Specific
How will you know you have achieved it?
Achievable
Realistic, within constraints
Relevant
To aims of the project
Measurable
It’s clear and precise.
When by?
Time-bound
Fits deadlines & time constraints

## Slide 12: Compare…
Identify system requirements.
Specify the requirements of the bus route planning system in an IEEE-format requirements specification by November 30th 2014.

## Slide 13: Are these good objectives?
Build a route planning system.
Literature Review.
To investigate the algorithms used in route planning.
Design a comparative study of pedestrian navigation using paper-based and phone-based maps
Become a better programmer.
Learn PHP.
Carry out user tests of the prototype.
Notes: How might they be improved. Are they SMART?

## Slide 14: f. Skills
List the skills needed
  Both current and those to be acquired
For each, show how it was /will be acquired
A table format is fine, e.g.
Structuring data with XML | To be learned by following online tuProject Proposalial at www.w3schools.com/xml
Java Programming | From modules Programming 1 & 2

## Slide 15: h. Resources
A bullet list is fine
What you need, why, where it is available.
Contingency plans?
“Samsung tablet with Android 4.2, to be provided by client. This is the implementation platform for the product. If unavailable, similar tablets are available for loan from Department of CSDT.”

## Slide 16: Resources – Things to consider
Software used MUST be legal & properly licensed.
Backups & Security are your responsibility!
What do you need?
  Consider using GitHub or similar.
  No allowance will be made for loss of data / programs.
Notes: Accidents do happen! As a computing student, you are expected to follow good practice regarding backups etc.

## Slide 17: i. Structure of your report
List planned chapter titles
  Descriptive titles
  Brief description
  May give main subsections
Check contents against marking scheme.
Cross-reference chapters to objectives.
List the appendices. Include :
  Project Proposal – first appendix
  Product documentation or other deliverables

## Slide 18: j. Marking scheme
Project type
Cross-reference chapters to marking scheme sections
One of:
  Product Marking Scheme (General and SE projects)
  Quality of Practical Work (Investigative Project)
Identify the deliverables / practical work to be assessed.
Identify assessment criteria – you will agree these with markers.

## Slide 19: j. What is the Product?
What is the main product?
What documentation will be produced together with the product? E.g.
  Specifications
  Models
  Test plans and results
These all form your product for marking.
Provide a list.

## Slide 20: j. Marking Scheme: Product
You may define criteria and weightings within these
Some are already defined, especially for SE project
If you don’t, defaults used.
See marking schemes
 | Fitness for Purpose | Build Quality
General Computing Project | 50% | 50%
Software Engineering Project | 40% | 60%

## Slide 21: j Marking Scheme: Quality of Practical Work
You MUST specify criteria on which practical work will be assessed
  Compliance with relevant ethical and safety guidelines (essential)
  Quality criteria related to deliverables
  Other quality criteria
Say what evidence will be provided
Criteria must allow you to demonstrate practical computing skills
(Investigative projects only)

## Slide 22: k. Project Plan (Gantt Chart)
Do(s)
  Include tasks that achieve each objective
  Sequence the tasks
  Use parallel tasks
  Estimate work hours & elapsed time
  Identify milestones
  Include report writing
Don’t(s)
  Over-complicate
Notes: List the tasks that are needed to achieve each objective - and no others
Don’t include unnecessary columns.

## Slide 23: If using MS Project
Use weekly timescale.
No more than 2 pages, please!
List the tasks that are needed to achieve each objective - and no others
List tasks names and time needed

## Slide 24: Work Breakdown Example
Break activities down far enough to let you see how you’re doing.
Notes: A good tool for getting started.

## Slide 25: Be realistic!
Ensure the project is achievable
  320 hours – minus lectures & what you’ve used so far
  Remaining weeks.
Be realistic about what you’ll do when
  Vacations
  Other deadlines

## Slide 26: Tying it all together
Ensure a clear correspondence between :
Project Objectives
Tasks in Project Plan
Chapters / Sections in Project Report
Mark Allocation
Ensure you plan to work on the objectives
Ensure you write up your work – cross-reference to objectives
Ensure you get marks for your work and write-up
Notes: A final check.

## Slide 27: Any Questions?